## Sheet1
# | Date of Query | Isuue Raised by | User Type | Query | Ansyst Remarks | Date of Resolution | Raj | Status
1 | 2021-10-30 | Raj Yadav |  | Skills Checklist: Need Search text Box AND We will remove Phone Number from it. Move Under applicants since it's not under job anymore. | Search box pending. | 2021-11-01 | I see it that we can search it within all the submitted skills checklist. | Open (VCS to provide input)
2 | 2021-10-30 | Raj Yadav |  | Manage Application: Default View shall be only for Open requisitions | Resolved. | 2021-11-01 |  | Resolved
3 | 2021-10-30 | Raj Yadav |  | Headers shall be fixed but rows shall be scrolled only | The bootstrap of portal template does not allow the same. If we change the CSS of bootstrap, then other design issues are arising. | 2021-11-01 |  | Closed
4 | 2021-10-30 | Raj Yadav |  | not Able to submit an offer/Offering screen. Error something went wrong | Not found any such case. | 2021-11-01 |  | Resolved
5 | 2021-10-30 | Raj Yadav |  | Onboarding+ Not Able to add/Create facility Specific document and Other documents. | Error not found. Kindly recheck again. If it's found then please send details with screenshot | 2021-11-01 |  | Resolved
6 | 2021-10-30 | Raj Yadav |  | As Applicant, Not able to upload any resume in PDF/Word under my profile or while applying | Not found any error. Tested and working properly. | 2021-11-01 |  | Closed
7 | 2021-10-30 | Raj Yadav |  | Not Able to see save button to save my entered information | Feature is already exists. Button name is now changed to "Save" | 2021-11-01 |  | Resolved
8 | 2021-10-30 | Raj Yadav |  | After few click Profile page got blank | Not able to find such cases. | 2021-11-01 |  | Closed
9 | 2021-10-30 | Raj Yadav |  | Applicants applying without Login are behaving differently for different users with the same role. Example: Submit button is not clickable with all mandatory details entered but after sometime we see 4 applications submitted from the same user. | Resolved. | 2021-11-01 |  | Resolved
10 | 2021-10-30 | Raj Yadav |  | Applicants applying with Login= Not Able to upload resume so not able to apply. We tried PDF and Word(10 different documents). Couldn't test the applicant further. Example: Submit button is not clickable with all mandatory details entered but after sometime we see 4 applications submitted from the same user. | Resolved. | 2021-11-01 |  | Resolved
11 | 2021-10-30 | Raj Yadav |  | Major Issue: When I apply without Login Then I can not sign up with the email ID as email ID exists AND neither I am able to login because email ID is invalid. So that applicant can never login in the portal now. | Resolved. | 2021-11-01 |  | Resolved
12 | 2021-10-30 | Raj Yadav | Recruiter | Do not see offer in summary to Accept for Few applicants "Offered" but sometimes we see for few applicants offered so behaviour is not consistent. | No such cases found. | 2021-11-01 |  | Closed
13 | 2021-10-30 | Raj Yadav | Recruiter | After Offer few fields missing data and sometime data is pre populated on the (fixing screen) like Pay rate, Client Name, Duration, Shift etc | Some data are auto-populated from posted job. Few fields whose data are not available yet, are left blank for fill-up. | 2021-11-01 |  | Closed
14 | 2021-10-30 | Raj Yadav | Recruiter | a few times it showed the error "Something went wrong" so couldn't even finish the popup fixing screen after offer; | This is not a system error. It's a message to say that either no response from backend server or internet connection is lost. | 2021-11-01 |  | Closed
15 | 2021-10-30 | Raj Yadav | Recruiter | Every time you fix the system the old posted jobs stay on our website but no application/applicant is visible and nothing works on it. | The issues are due to recent changes in application. Once we clean the database after UAT, the problem will be resolved. | 2021-11-01 |  | Closed
16 | 2021-10-30 | Raj Yadav | Onboarding | Not able to add Client specific document and Other document before sending to applicant. | Resolved. | 2021-11-01 |  | Resolved
17 | 2021-10-30 | Raj Yadav | Onboarding | Will be good to allow "Action button" all time with Onboarding, Hire, Completed onboarding as we might need to request more documents after a few months if anything expires from the provided list of documents. | The documents for applicants can be uploaded later also from Applicant submodule. (Link: Applicant > Action > Upload Apl Docs). But if we keep the process open for "Onboarding ..." as you suggested, then it process consistency in this software will be impaired. | 2021-11-01 | These documents get expired in timeframe so we have have to request few docs again from candidate while they are working so allowing to request more doc so applicant can upload will be good. So requested to still have the option under Action item. | Open (VCS to provide input)
18 | 2021-10-30 | Raj Yadav | Finance | Hired many applicants in the right week but when trying to process payroll then the Popup window does not display any row of data of the Hired Candidate so not able to create/process payroll. So Not Able to test further. | Recommened to full demonstration from Ansyst team. | 2021-11-01 | Tried and worked for Nov 1st week for NYCHH but were not showing any candidate in Oct payroll even if few people stated in oct. May be data issue but can show you defect. | Open (VCS to provide input)
19 | 2021-10-30 | Raj Yadav |  | Please do not use Recruitee instead use Applicant. | To be done. | 2021-11-01 |  | Open
20 | 2021-10-30 | Raj Yadav |  | It will be good allow filtering job based on Status and By default jobs shawn are "Open". We will have over 100+ posting per day so will be good to search based on existing search but also Status will help us keep the screen clean with open jobs only as default view. | Searching Option on Status will be added. | 2021-11-01 |  | Open
21 | 2021-10-30 | Raj Yadav |  | We can remove Position Tupe field from a Job and other screens and dropdown since it is looking extra as "title" is already text type for it. | Position Type has different meaning than Job Title. In every job portal /template, job Position is most important field. If you suggest, we'll remove the Position. As it's linked to many pages, so it requires time to fix. And further it'll not be reverted back. Please reconfirm the same. | 2021-11-01 | I withdraw this change. We are ok with current options. | Closed
22 | 2021-11-01 | Druv Bindra |  | Can you please add the following page on the resources link tab under healthcare. | To be done. | 2021-11-01 |  | Open
23 | 2021-11-07 | Raj Yadav |  | Applied Raj Yadav on ICU of MT Sinai recruiter rejected the candidate and Raj yadav data from "new App" and Submission is Removed. Now I click on the summary but I see Raj Yadav offered. | To be done. |  |  | Open
24 | 2021-11-08 | Raj Yadav |  | As Applicant, I was able to upload jpeg for 1 document but for 2nd document I got bellow error messages. tried same JpEG and different too but did not work out | To be done. |  |  | Open
25 | 2021-11-08 | Raj Yadav |  | no status displayed for aplicant applications. Example: Rejected status not displayed on candidate applications | To be done. |  |  | Open